## Start Here
Trade Job Quote & Change Order Workbook
by Knackdesk · knackdesk.com
HOW TO USE
1. Settings: your labour cost rate, overhead percentage, target profit margin, markups for change orders and subcontractors, and the deposit share.
2. Quote: list materials (quantity × unit cost), labour tasks (hours at your cost rate) and subcontractors. Overhead and margin roll up into the quote price, profit, markup and deposit. Copy the sheet for each new quote.
3. Change Orders: one row per change with materials, hours and subcontractor cost. Your markups give the change price; the revised contract total updates after every row.
4. Jobs: one row per job with quoted price, change orders, actual materials, hours and subs, invoiced and paid. Cost, overhead, profit, margin and outstanding are calculated.
5. Summary: totals and margins across jobs, outstanding balances and how many jobs fell below the target margin.
LEGEND
Blue text = a cell you type into. Black text = a formula, leave it alone. Yellow fill = key inputs.
Blue cells that already contain a formula (rates and markups pulled from Settings) may be overwritten per line.
DEFINITIONS
Direct cost = materials + labour hours × cost rate + subcontractors. Overhead = direct cost × overhead %. Total cost = direct + overhead.
Quote price = total cost ÷ (1 − margin %). Profit = price − total cost. Markup = profit ÷ total cost.
Change price = (materials + hours × rate) × (1 + markup) + subs × (1 + sub markup). Revised total = original + all change orders.
Fixed figures, before tax. Arithmetic only; not legal, contract or tax advice. Support: hello@knackdesk.com

## Settings
Settings
Labour cost rate per hour | 45 | What an hour costs you: wages, contributions, paid downtime. Not what you charge.
Overhead (% of direct cost) | 15 | A year of overhead ÷ a year of direct job cost.
Target profit margin (% of price) | 20 | Profit as a share of the quote price.
Subcontractor markup (%) | 10 | Applied to subcontractor cost on quotes and change orders.
Change-order markup on own work (%) | 35 | Markup on materials and labour in change orders; usually your standard markup.
Deposit (% of quote) | 30 | Shown on the quote as the deposit to request.

## Quote
Quote
Client | Example Homeowner
Job | Kitchen refit
Material | Quantity | Unit cost | Line cost
Base units | 6 | 95 | 570
Worktop (m) | 4 | 60 | 240
Fixings and sundries | 1 | 120 | 120
Labour task | Hours | Cost rate | Labour cost
Strip out | 4 | 45 | 180
Fit units and worktop | 10 | 45 | 450
Finishing | 2 | 45 | 90
Subcontractor | Cost
Electrician | 300
Materials | 930
Labour | 720
Subcontractors (at cost) | 300
Direct cost | 1950
Overhead | 292.5
Total cost | 2242.5
QUOTE PRICE | 2803.13
Profit | 560.63
Markup on total cost % | 25
Deposit to request | 840.94
Subcontractors are priced at cost here and covered by the margin; apply a separate sub markup on change orders.

## Change Orders
Change Orders
Original contract price | 2803.13
# | Description | Materials | Hours | Cost rate | Subcontractors | Own cost | Own markup | Sub markup | Change price | Revised contract total | % of original
1 | Extra double socket | 40 | 1.5 | 45 | 120 | 107.5 | 37.63 | 12 | 277.13 | 3080.26 | 9.89
2 | Upgrade worktop | 260 | 2 | 45 | 0 | 350 | 122.5 | 0 | 472.5 | 3552.76 | 16.86
Totals | [8 empty] | 749.63
Revised contract total | [8 empty] | 3552.76
All changes as % of original | [8 empty] | 26.74
Note on B2: Defaults to the Quote sheet; overwrite with the signed contract figure.

## Jobs
Jobs
One row per job. Enter actual materials, hours and subcontractor cost as the job runs; profit and margin update.
Job | Client | Status | Quoted price | Change orders | Contract total | Actual materials | Actual hours | Cost rate | Actual subs | Direct cost | Overhead | Total cost | Profit | Margin % | Invoiced | Paid | Outstanding
Kitchen refit | Example Homeowner | active | 3000 | 450 | 3450 | 980 | 18 | 45 | 300 | 2090 | 313.5 | 2403.5 | 1046.5 | 30.33 | 3450 | 1035 | 2415
Bathroom tiling | Sample Ltd | done | 1800 | 0 | 1800 | 520 | 14 | 45 | 0 | 1150 | 172.5 | 1322.5 | 477.5 | 26.53 | 1800 | 1800 | 0
Garden wall | Demo Client | done | 2400 | 200 | 2600 | 900 | 20 | 45 | 250 | 2050 | 307.5 | 2357.5 | 242.5 | 9.33 | 2600 | 2600 | 0
Totals |  |  | 7200 | 650 | 7850 | 2400 | 52 |  | 550 | 5290 | 793.5 | 6083.5 | 1766.5 | 22.5 | 7850 | 5435 | 2415

## Summary
Summary
Jobs tracked | 3
Contract value (quotes + change orders) | 7850
Total cost including overhead | 6083.5
Profit | 1766.5
Overall margin % | 22.5 | profit ÷ contract value
Target margin % (Settings) | 20
Jobs below the target margin | 1
Change orders as % of quoted prices | 9.03
Hours worked | 52
Average profit per hour | 33.97 | profit ÷ hours
Invoiced | 7850
Paid | 5435
Outstanding | 2415